## Sheet1
Problem Description | Bug/Enhancement | Severity(H,M,L) | Report date | Reported By | Owner | Notes | Update | Action | Fixed in
Ap crashes in setSelectedRegistrar | Bug | M | 2006-06-01 | Laura Wang |  | Not in beta version
Added more than one enrollee, if error, can't recover. | Enhancement | L | 2006-06-01 | Laura Wang |  | Once error is made by user, can't recover.
USB mount device is hard coded | Enhancement | L | 2006-06-01 | Laura Wang |  | Should be trivial
Use USB to tansfer config, not Pin | Enhancement | L | 2006-06-01 | Laura Wang |  |  | We have added this feature for unencrypted settings.
No response for getDeviceInfo | Bug | M | 2006-06-01 | Laura Wang |  | With Vista as Registrar
1a, after config, add enrollee | Enhancement | L | 2006-06-01 | Laura Wang
After config AP, should assign new SSID, but it still write out old SSID | Bug | L | 2006-06-01 | Laura Wang |  | Sent email to ask for more details.
When pass phrase is used for PSK, use ' ' around PSK |  | L | 2006-06-01 | Laura Wang |  | Sent email to ask for more details.
Buffers are often allocated with new char[len], but freed with a non-array delete operator | Bug | H | 2006-06-05 | Vic Lortz |  | Recommended resolution is to use malloc/free instead.
Bug in the UFD unencrypted settings code: will not support passcode credentials. Hard-coded memcpy( p_cbMsg->nwKey, nwKey,SIZE_64_BYTES ); // memcpy() size parameter should be changed to use nwKeyLen. This problem occurs in two places in MasterControl.cpp. | Bug | M | 2006-06-05 | Vic Lortz
Only one Registration Protocol instance is supported at a given time by the state machines. This means simultaneous attempts to connect might interfere with each other. It also means the rekeying feature envisioned in the spec won’t work, because that event would trigger simultaneous attempts to reconnect. | Enhancement | m | 2006-06-05 | Vic Lortz
In some cases, if an AP is rebooted, a Registrar connected to that AP over Ethernet will call GetDeviceInfo on the AP using UPnP but deliver the M2 message to PutWLANResponse rather than PutMessage. | Bug | M | 2006-05-24 | Ubicom (Freeman) |  | Proposed fix made, but no yet tested.